AI x CITY CLIMATE ACTION HACKATHON 2026

FloodFact AI

Pilot Plan

Phase 1 — Mukuru, Nairobi (kwa Reuben · kwa Njenga · Viwandani)

Prepared September 2026  ·  Repository: github.com/VinceOdundo/FloodfactAI

Companion documents: FloodFact-AI-Concept.pdf · FloodFact-AI-Demonstration.pdf

Team: Samuel Mburu Kairu · Vincent Odundo · Alvin Nyota · Amani Maria — Nairobi, Kenya

# 1. Executive Summary

FloodFact AI is a community-centered flood early-warning and WhatsApp-rumour-verification system built for Nairobi's informal settlements. This Pilot Plan sets out the 4-week Phase 1 pilot in Mukuru, Nairobi, exactly as scoped in the FloodFact AI Requirements Specification (§11, Pilot Scope), and shows how the system already built for this submission — real database schema, a deterministic and unit-tested risk-scoring core, and a working admin, ambassador, and public product — satisfies each of the Requirements Specification's 12 Phase 1 MVP acceptance criteria (§18).

The system is code-complete and already runs live on 4 of 5 external integrations (Africa's Talking, Anthropic Claude, Voyage AI, and Esri ArcGIS — only the Meta WhatsApp Cloud API remains to be provisioned), backed by a real, migrated Supabase project (see the Demonstration submission). Turning it on for a real pilot is a deployment and partnership-confirmation exercise, not a rewrite: every external dependency already has a working adapter, and docs/SETUP.md walks through provisioning each one.

## 1.1 Pilot Scope

| Item | Pilot definition |
| --- | --- |
| Area | Mukuru: kwa Reuben, kwa Njenga, Viwandani |
| Duration | 4-week demo · September–October 2026 |
| Target | 500 households, Phase 1 |
| Ambassadors | 10 trained youth per ward (30 total) |
| Channels | WhatsApp + SMS + 3 community notice boards |
| Data | ArcGIS Living Atlas + Kenya Meteorological Department (KMD) |
| Trigger | Short rains season, October onset |

Source: FloodFact AI Requirements Specification §11 — Pilot Scope.

## 1.2 Success Targets

| Target | Tracked via |
| --- | --- |
| 80% of households receive alerts within 30 minutes | pilot_metrics.alerts_within_30min_pct — live SQL view, Admin → Pilot Metrics |
| 50% reduction in rumour spread in pilot zones | pilot_metrics.false_information_rate_pct trend + ambassador household spot-checks |
| 100% of ambassadors trained in AI tool use | pilot_metrics.ambassadors_trained_pct — driven by ambassadors.training_status |

Source: FloodFact AI Requirements Specification §4 — Goals (Pilot impact).

# 2. Activities & Timeline

Four weeks, timed to the short-rains onset named in the Requirements Specification's pilot trigger. Every week's exit criteria are checked against real system state — the escalations queue, data-source health panel, and pilot_metrics view — not a status update typed by hand.

## Week 1 — Setup & Training

- Deploy the production Supabase project, apply the 6 Supabase migrations, and seed the 3 pilot areas — following docs/SETUP.md.

- Already mostly live: Africa's Talking, Anthropic, Voyage AI, and the ArcGIS flood-risk layer (WRI Aqueduct) are live — provision the remaining WhatsApp Cloud API credential and confirm the KMD data-sharing arrangement (open item, §19).

- Recruit and train 30 youth ambassadors (10 per ward) on the ambassador PWA, ground-truth logging, and escalation handling.

- Confirm the Mukuru gazetteer and safe-zone locations with local ambassador knowledge, and install the 3 physical community notice boards.

## Week 2 — Soft Launch (Shadow Mode)

- Open WhatsApp, SMS, and web intake to a limited set of households per ward.

- Admin team reviews every classification in shadow before it reaches the public alerts feed, to validate risk-engine calibration against local ground truth.

- Daily stand-up reviewing the escalations queue and the data-source health panel.

- Iterate on gazetteer coverage and alert wording based on ambassador and household feedback.

## Week 3 — Full Operation

- Full 500-household rollout across all three wards; shadow review is lifted.

- Verified and elevated-risk classifications publish directly; the system still routes insufficient_evidence and high-impact cases to a human, per acceptance criterion 12.

- Daily tracking of the three Requirements-Specification success targets via the live dashboard.

- Weekly community notice-board refresh as new reports and ambassador ground-truth confirm or correct earlier claims.

## Week 4 — Evaluation & Handoff

- Compute final pilot_metrics across all three wards from recorded reports, classifications, and ambassador_observations — acceptance criterion 10.

- Run an ambassador debrief and a household spot-check survey, as the direct proxy for the rumour-reduction target.

- Compile a findings report against every Requirements-Specification acceptance criterion and goal — see §6 of this plan.

- Present the roadmap for Phase 2 (additional hazards) and Phase 3 (national scale) — see §8.

# 3. Team Structure & Roles

## 3.1 Pilot Delivery Team

Lean by design — a startup team, not a large program office. Ambassador redundancy (10 per ward, not 1) is deliberate: it is the mitigation for the single highest-likelihood pilot risk (see §7).

| Role | Count | Responsibility |
| --- | --- | --- |
| Pilot Lead | 1 | Overall delivery owner; partner and city liaison; final escalation point. |
| Engineering / Platform Lead | 1 | Owns deployment, credential provisioning, data-source health, and fixes. |
| Ward Ambassador Coordinator | 3 (1/ward) | Manages and schedules that ward's 10 ambassadors; runs daily check-ins. |
| Youth Ambassador | 30 (10/ward) | Ground-truth verification, community trust layer, notice-board upkeep. |
| M&E / Data Analyst | 1 | Owns pilot_metrics reporting and the acceptance-criteria evaluation report. |
| Partnerships & Data Liaison | 1 | Manages ArcGIS Living Atlas / KMD relationships and messaging-provider accounts. |

## 3.2 System User Roles

The roles the running product itself is built for, distinct from the delivery team above.

| Role | Needs / responsibilities |
| --- | --- |
| Resident | Submit a flood report, warning, or suspicious message; receive verified alerts and recommended actions. |
| Youth Ambassador | Receive community reports, support ground validation, explain results locally, distribute trusted information. |
| System / Operations Admin | Monitor incoming reports, verification status, alerts, data-source health, audit logs, pilot metrics. |
| Data / Climate Source | Provide machine-readable or operator-accessible weather, rainfall, flood-risk, river, and historical information. |
| Partner / Emergency Stakeholder | Receive or review verified alerts and coordinate response where appropriate. |

Source: FloodFact AI Requirements Specification §5 — Users and Roles.

# 4. Data & Partner Dependencies

Every row below already has a working code adapter. “Status for pilot” states plainly what is real today versus what needs a pilot-time decision — including the two data sources the Requirements Specification itself flags as still to be confirmed (§19).

| Source | Role in the system | Status for pilot |
| --- | --- | --- |
| Open-Meteo | Rainfall, forecast, ERA5 reanalysis evidence | Live today — free, keyless public API |
| Esri ArcGIS Living Atlas | Flood-risk zone evidence | Live — WRI Aqueduct 3.0 riverine flood-risk layer, found via the hackathon's own ArcGIS Hub; queryable anonymously |
| Kenya Meteorological Department (KMD) | Regional advisory / rainfall corroboration | Named in pilot scope; data-sharing arrangement to be confirmed (§19) |
| Meta WhatsApp Cloud API | Resident report intake + alert delivery | Free test number ready; production verification needed for full reach |
| Africa's Talking | SMS report intake + alert delivery | Live — sandbox account credentials verified with real API calls; a production account is the only remaining step before real SMS delivery |
| Anthropic Claude | Structured claim extraction + rationale text (never the verdict) | Live — API key verified with a real call |
| Voyage AI + pgvector | Rumor-pattern similarity matching | Live — API key verified with a real embeddings call |
| Supabase | Postgres + PostGIS + pgvector + Auth + Realtime, RLS on every table | Live — real project provisioned and migrated (9 migrations, RLS on every table) |

# 5. Acceptance Criteria Traceability

All 12 Phase 1 MVP acceptance criteria from the Requirements Specification, mapped to the real code and schema that already satisfy each one.

| # | Requirement | How the system satisfies it |
| --- | --- | --- |
| 1 | A resident can submit a WhatsApp or SMS report and the system creates a trackable case. | Webhook routes (whatsapp, africastalking) + the public /api/reports route all write a validated reports row. |
| 2 | A report can be associated with a pilot area where location is available. | lib/core/geocode.ts matches claimed location text against the Mukuru gazetteer and resolves pilot_area_id via PostGIS. |
| 3 | The verification workflow can retrieve and record evidence from configured data sources. | lib/pipeline/classify.ts fetches rainfall, flood-risk, historical, corroboration, and ambassador signals in parallel; every fetch — success, failure, or sandbox — becomes an evidence_items row. |
| 4 | The system produces one of the three defined classifications. | lib/core/risk-engine.ts scoreReport() returns Verified Warning, Elevated Risk, or False Information — deterministic, 23 unit tests. |
| 5 | The system records a reason/evidence summary for the classification. | classifications.rationale_en (bilingual) plus evidence_snapshot (jsonb) and engine_version are stamped on every verdict. |
| 6 | A verified/elevated-risk result can be transformed into an actionable alert. | lib/core/alert-templates.ts builds a channel-specific, classification-keyed message. |
| 7 | Alerts can be sent through at least the configured pilot channels that are technically available. | alert_deliveries records per-channel status for WhatsApp, SMS, and the ambassador queue. |
| 8 | Youth ambassadors can receive/annotate relevant cases. | The ambassador PWA + ambassador_observations table, RLS-scoped to each ambassador's own pilot_area_id. |
| 9 | All key report, verification, classification and alert events are logged. | audit_events is append-only — no UPDATE/DELETE grant to any role. |
| 10 | Pilot metrics can be calculated from recorded events rather than manually typed demo values. | pilot_metrics is a SQL view computed live from reports, classifications, alerts, and ambassador_observations. |
| 11 | The system handles unavailable/conflicting data without falsely claiming certainty. | insufficient_evidence is a distinct boolean that can never silently collapse into False Information — enforced by dedicated unit tests. |
| 12 | An operator can review and override/escalate an uncertain or high-impact case. | The escalations table + Admin → Escalations page require a resolution note before a human can close a case. |

Source: FloodFact AI Requirements Specification §18 — Acceptance Criteria for Phase 1 MVP.

# 6. Risk Register

| Risk | Mitigation |
| --- | --- |
| KMD data-sharing arrangement not finalized before pilot start (the ArcGIS flood-risk layer is resolved — live today, WRI Aqueduct). | Open-Meteo (real, keyless) and the now-live ArcGIS layer already cover rainfall and flood-risk evidence for real; only the KMD regional-advisory corroboration remains open. |
| WhatsApp Cloud API's free test tier caps recipients before production verification completes. | SMS via Africa's Talking and the public web form remain fully functional fallback channels throughout. |
| Risk-engine miscalibration in the pilot's early days. | Week 2 shadow-mode human review of every classification before any goes live publicly; 23 unit tests already cover the documented safety rules. |
| Low household smartphone/data access limits WhatsApp reach. | SMS plus 3 physical community notice boards per ward; ambassadors as an in-person channel of last resort. |
| Ambassador attrition or unavailability during the 4-week window. | 10 trained ambassadors per ward, not 1, gives built-in redundancy; training materials are reusable for fast onboarding of a replacement. |
| Short-rains onset timing shifts outside the planned 4-week window. | The system and ambassador workflow stay operational at low intake volume regardless; the pilot period can extend with no code change, since hazard type and pilot area are data, not code. |

# 7. Cost & Scale

Every provider chosen for Phase 1 has a free or sandbox tier sufficient for 500 households. The architecture already generalizes — hazard_type and pilot_area are data, not code — so scaling is a provider-tier and message-volume question, not a rewrite. Dollar figures below are illustrative order-of-magnitude, pending final provider quotes at each tier.

| Scale | Compute / database | Messaging | AI (LLM + embeddings) |
| --- | --- | --- | --- |
| 500 households (Phase 1 pilot) | Vercel Hobby + Supabase Free — $0 | WhatsApp Cloud API free test tier + Africa's Talking sandbox — near $0 | Pay-per-token, low volume — low single-digit $/month |
| 5,000 households (Phase 2) | Vercel Pro + Supabase Pro — needed for backups and connection limits | WhatsApp/SMS production pricing becomes the largest line item | Same providers, ~10× token volume |
| 50,000 households (Phase 3, national) | Supabase scaled tier / read replicas — same codebase, no rewrite | Messaging cost dominates total spend, not engineering | Batched extraction keeps marginal LLM cost per report low |

# 8. Post-Pilot Roadmap

- Phase 2 — Add landslide and fire hazards — new provider adapters and rows, same pipeline. No rewrite: hazard_type is data.

- Phase 3 — Expand to SMS, radio, TV, and USSD channels at national scale across Nairobi's informal settlements.

## Appendix — Companion Materials

- Concept: Problem, functionality, and innovation narrative — FloodFact-AI-Concept.pdf.

- Demonstration: Real screenshots of the running product, end to end — FloodFact-AI-Demonstration.pdf.

- Repository: Full source, migrations, tests, and docs/SETUP.md for going live — github.com/VinceOdundo/FloodfactAI.